## README
Team Capacity Planner
Free template from spreadsheet.partners — free for commercial use, no attribution needed.
What this workbook is for
Allocating work against hours that actually exist. Contracted hours are not available hours: leave, standups, reviews, recruitment, support rotas and admin come out first. The agency in the worked example planned a 40-hour week, reported 90% utilisation and still missed dates — after subtracting leave and non-project time there were 30 available hours against 36 committed, so real utilisation was 120% and nobody was underperforming.
What counts as non-project time
Everything you are paid for that is not allocated to a project: standups, planning and retros, code or design review, internal meetings, 1:1s, recruitment and interviews, support and on-call, training you deliver, line management, expenses and timesheets, and the recovery time around all of it. It is not leave — leave has its own tab — and it is not slack you can spend.
How to calibrate it, rather than guess
Measure it for two weeks. Ask everyone to log only two buckets, project and not-project, at the end of each day; two weeks is enough and a month is never finished. Most teams land at 15-20% of contracted hours, and most plans had assumed 5%. That 10-15 point gap is the whole difference between a plan that holds and one that slips. Re-measure when the shape of the team changes — a new joiner, an on-call rota, a support contract — not on a calendar.
One row per person per month
The Capacity sheet is keyed on person AND month, because allocation is. Set up the people you plan for and repeat them for each month you plan ahead: twenty people and ten months is 200 rows, which is what the sheet holds. Copy a month's block down and change the month rather than retyping.
Which columns you type
Capacity: A Person, B Month, C Contracted, E Non-project, M Role, N Notes, plus the two thresholds in C3 and G3 and the summary month in P2. Allocations: A-F. Leave: A-E and I. Heatmap: the names in column A and the first month in B4. Everything else is calculated — yellow means type here, black means leave it alone.
Why Leave is not typed on the Capacity sheet
Column D is a SUMIFS over the Leave tab, keyed on person and month, so a booking made in one place cannot disagree with the other. Book the absence on the Leave tab and the hours appear here. Leave that crosses a month end needs two rows, one per month, because the month key is taken from the first day. Working days come from NETWORKDAYS, so a week off is five days, not seven; hours per day is a column so four-day weeks and part-timers work.
The utilisation bands
Target 80% and ceiling 85% are typed in C3 and G3, not hard-coded. 70-80% of available hours is realistic for delivery roles. Above the ceiling there is no absorption capacity at all: illness, a support escalation or one rework cycle turns immediately into a missed date. A row reading 'No slack' is not a problem yet; a row reading 'Overallocated' is committed work that will not happen.
Overallocation is reported in hours
Column I, and the second grid on the Heatmap, give hours rather than a percentage. 'Two people are 18 hours over' is a conversation with an obvious resolution; 'we are a bit stretched' is not one. The fix is on the Allocations tab — move hours, move the date, or take the provisional work out — not by editing a number here.
Part-time people
Change the contracted hours and nothing else. Every downstream formula works from available hours, so a 0.8 FTE at 128 contracted hours is handled identically to a full-timer once availability is calculated. The same is true of a mid-month joiner: pro-rate the contracted hours for that month.
Provisional work still consumes hours
An allocation marked Provisional is included in the totals on purpose. Work you are 70% likely to win is not 0% of a person's month, and plans that exclude it look fine until the week the proposal is accepted. Take it out when it is lost, not before.
The 'No capacity row' check
Column I on Allocations flags a person-and-month combination that does not exist on the Capacity sheet. Those hours are allocated to nobody: they are in no total, no heatmap cell and no utilisation figure, and the plan looks healthier than it is. It is almost always a name typed two different ways.
Ranges
Capacity, Allocations and Leave all cover rows 5-204. Insert rows inside that range rather than typing below it, or the summaries and the heatmap will not see the new data. Months are real dates displayed as yyyy-mm — type 2026-07 and the sheet stores the first of the month. Percentages are stored as fractions: 0.85 displays as 85.0%.
Blue text on a yellow fill = type here. Black = calculated, leave alone.

## Capacity
Capacity
One row per person per month. Type A, B, C and E. Leave comes from the Leave tab, Allocated from the Allocations tab, and everything from F onwards is calculated. | [13 empty] | Month to summarise | 2026-07-01
Target utilisation |  | 80% |  | No-slack ceiling |  | 85% |  | 70-80% is a realistic target for delivery roles; above the ceiling any variation turns straight into a missed date.
Person | Month | Contracted | Leave (h) | Non-project (h) | Available | Allocated | Utilisation | Over (h) | Spare (h) | Status | Projects | Role | Notes |  | This month | Value
A. Duval | 2026-07-01 | 160 |  | 24 | [7 empty] | Delivery lead | Two projects plus line management |  | People with a capacity row
K. Owens | 2026-07-01 | 160 |  | 20 | [7 empty] | Consultant |  |  | Contracted hours
M. Ferrer | 2026-07-01 | 128 |  | 18 | [7 empty] | Consultant (0.8) | Four days a week — part-time shows up in Contracted only |  | Leave booked
S. Novak | 2026-07-01 | 160 |  | 22 | [7 empty] | Engineer |  |  | Non-project time
Available hours
Allocated hours
Team utilisation
Hours overallocated
Hours spare
People over their available
People above the ceiling
Available hours lost to leave
Non-project share of contracted
If 'non-project share' is under about 10% the figure is a guess, not a measurement. Most teams land at 15-20%.

## Allocations
Allocations
One row per person, project and month. Type A-F. G onwards is calculated from Capacity. Split a piece of work that spans two months into two rows.
Person | Project | Month | Hours | Status | Notes | Their available (h) | Share of their month | Check
A. Duval | Meridian rollout | 2026-07-01 | 90 | Confirmed | Phase 2 delivery
A. Duval | Halcyon migration | 2026-07-01 | 44 | Confirmed | Technical lead, two days a week
K. Owens | Kestrel proposal | 2026-07-01 | 72 | Provisional | Not signed — comes off if the proposal is lost
K. Owens | Internal tooling | 2026-07-01 | 40 | Confirmed
M. Ferrer | Ardent support | 2026-07-01 | 60 | Confirmed | Retainer, fixed hours
M. Ferrer | Meridian rollout | 2026-07-01 | 38 | Confirmed
S. Novak | Halcyon migration | 2026-07-01 | 104 | Confirmed | Full-time on the migration

## Leave
Leave
Booked absence. Type A-E and I; working days, hours and month are calculated. Leave that crosses a month end goes in two rows, one per month.
Person | Type | First day | Last day | Hours per day | Working days | Hours | Month | Notes | Leave booked, by person
A. Duval | Holiday | 2026-07-13 | 2026-07-14 | 8 |  |  |  |  | Person | Days | Hours
M. Ferrer | Training | 2026-07-03 | 2026-07-03 | 8 |  |  |  | Certification day — booked by the client | A. Duval
S. Novak | Holiday | 2026-07-20 | 2026-07-24 | 8 |  |  |  | Full week | M. Ferrer
S. Novak
Formulas:
Working days = IF([Person]="","",IF(OR([First day]="",[Last day]=""),"",NETWORKDAYS([First day],[Last day])))

## Heatmap
Heatmap
Utilisation by person and month. Type the first month in B4 and the names in column A; the other eleven months follow automatically.
Person | 2026-07-01
A. Duval
K. Owens
M. Ferrer
S. Novak
Overallocation in hours — the same grid, in the unit people argue about
Person
Whole team, by month
Measure
Available hours
Allocated hours
Utilisation
Hours over
Hours spare
People over
Leave hours