## README
Event Planning & Logistics
Free template from spreadsheet.partners — free for commercial use, no attribution needed.
What this workbook is for
Running an event backwards from its date. Every task carries a lead time in days rather than a due date, and the due date is calculated as the event date minus that lead. When the 300-person conference on the template page moved back three weeks because a keynote dropped out, the whole schedule reflowed from one cell and only two tasks needed a phone call.
The one cell that matters
Tasks!B3 is the event date, and it is named EventDate. Every due date on the Tasks tab and every 'lead from event' on the Suppliers tab is derived from it. Change it and the plan reflows. Do not type a date into column D — it is calculated, and typing over it breaks exactly the thing the template is for.
How lead times were set
A lead time is 'how long before the event this has to be finished', counted in calendar days. The four seeded rows come from the template page: venue 90, registration open 60, final catering count 7, badges printed 3. Set yours from the supplier's own requirement, not from when you would like to do it — if the printer needs three working days from artwork approval, the badge task is lead 3 and the artwork task is lead 6 or more.
Which lead times are contractual
Mark those Critical. They are the ones with an external deadline attached to money: the venue contract and its cancellation dates, the catering guarantee (the number you give is the number invoiced, whoever turns up), a print run, a flight booking, an insurance cut-off. Internal tasks — drafting a running order, briefing the crew — can almost always absorb a day and should not be critical. The summary on the Tasks tab counts critical tasks separately for that reason: three open internal tasks is a normal Tuesday, one open critical task is a phone call now.
Working-day due dates
Column G takes the calculated due date and, if it lands on a Saturday or Sunday, pulls it back to the Friday. WORKDAY with a holiday list would be the textbook formula and it is not available in every version this file has to open in, so the weekend shift is done with WEEKDAY instead. Public holidays are not modelled: add them to the lead time of the tasks they affect, which is where a supplier's own shutdown belongs anyway.
Which columns you type
Tasks: the event date in B3, then A Task, B Owner, C Lead, E Status, F Critical, J Category, K Supplier, M Notes. Budget: A-F, J, and the category list in column L. Suppliers: A-G, I, L, O. Attendees: A-J and M. Everything else is calculated — yellow means type here, black means leave it alone.
Budget consumption is read by category, not by line
The block to the right of the Budget lines divides actual by planned for each category, which is the level at which overspend is actually managed. A single line over by 200 is noise; a category at 120% is a conversation. Committed is the middle column and the one people skip: money you have signed for and not yet been invoiced is spent, and a category that looks 40% consumed with every contract signed is fully committed.
Keep the category lists identical
Tasks, Budget and Suppliers all use the same category list. Add a category in one place and you have to add it in the other two, or the roll-up silently misses lines. The lists are drop-downs to make that harder to get wrong.
Suppliers and contract deadlines
Column J tells you how many days before the event a supplier's deadline falls; that number is the lead time for the matching task on the Tasks tab, which is how the two tabs stay in step. The flag turns to 'Decide now' inside fourteen days and to 'DEADLINE PASSED' after, unless the status is Confirmed.
Attendees, catering and access
The catering count is confirmed plus registered, because that is the number the caterer is given seven days out and the number that gets invoiced whoever turns up. The dietary breakdown to the right of the list is the caterer's brief. The 'Needs check' column flags anyone with an access requirement or a dietary one, so the person on the door has a short list rather than a spreadsheet. Cancelled rows stay on the sheet and are excluded from every count.
Ranges
Tasks, Budget, Suppliers and Attendees all cover rows 5-204. Insert rows inside that range rather than typing below it, or the summaries will not see them. For an event with more than 200 attendees, extend the Attendees ranges or keep the registration list in the ticketing system and import the totals. Percentages are stored as fractions: 0.9 displays as 90.0%.
Blue text on a yellow fill = type here. Black = calculated, leave alone.

## Tasks
Tasks
Type the event date in B3 and a lead time per task. Every due date is derived from those two numbers, so moving the event moves the whole plan.
Event date | 2026-09-10 | Named EventDate. Change this one cell and every due date below reflows.
Task | Owner | Lead (d) | Due | Status | Critical | Due (working day) | Days left | Flag | Category | Supplier | Check | Notes | Due if still open | The plan | Value
Confirm venue | M. Ferrer | 90 |  | Done | Yes |  |  |  | Venue | Northgate Hall |  | Contract signed. Cancellation terms bite from 60 days out. |  | Event date
Open registration | K. Owens | 60 |  | Done | Yes |  |  |  | Marketing |  |  | Landing page live; capacity capped at 300. |  | Days to go
Final catering count | M. Ferrer | 7 |  | Open | Yes |  |  |  | Catering | Bellhouse Catering |  | Contractual guarantee — the number given is the number invoiced. |  | Tasks on the plan
Print badges | A. Duval | 3 |  | Open | No |  |  |  | Print | Quickprint Ltd |  | Can slip a day; badges can be handwritten at the desk if it comes to it. |  | Done
Not started or open
Blocked
Complete
Overdue
Due this week
Critical tasks
Critical still open
Critical overdue
Tasks with no owner
Next deadline still open
Last task before the event
'Next deadline still open' is the earliest due date among tasks that are neither Done nor Not needed, taken from the helper in column N.
Formulas:
Days left = IF([Due]="","",IF([Status]="Done","",[Due]-TODAY()))
Flag = IF([Task]="","",IF(OR([Status]="Done",[Status]="Not needed"),"",IF([Due]="","",IF([Due]<TODAY(),"OVERDUE",IF([Due]-TODAY()<=7,"Due this week","")))))

## Budget
Budget
One row per budget line. Type A-F and J. The category summary to the right rolls these up and is where budget consumption is read.
Category | Line item | Supplier | Planned | Committed | Actual | Over/(under) | Variance % | Status | Notes | Category | Planned | Committed | Actual | Consumed | Remaining | Open tasks | Status
Venue | Northgate Hall — main hall, full day | Northgate Hall | 9500 | 9500 | 9500 |  |  |  |  | Venue
Venue | Breakout rooms x2 | Northgate Hall | 1800 | 1800 | 1800 |  |  |  |  | Catering
Catering | Lunch and two breaks, 300 covers | Bellhouse Catering | 12000 | 12000 | 0 |  |  |  |  | AV & production
Catering | Speaker dinner, 14 covers | Bellhouse Catering | 900 | 900 | 0 |  |  |  |  | Speakers
AV & production | Stage, screens, two technicians | Stagecraft AV | 7400 | 7400 | 3700 |  |  |  |  | Marketing
Speakers | Keynote fee and travel |  | 4500 | 4500 | 4500 |  |  |  |  | Print
Marketing | Paid social and email campaign |  | 3000 | 0 | 2150 |  |  |  |  | Travel
Print | Badges, signage, programmes | Quickprint Ltd | 1600 | 1600 | 0 |  |  |  |  | Staffing
Staffing | 6 crew for two days |  | 2400 | 0 | 0 |  |  |  |  | Insurance
Insurance | Event liability cover |  | 650 | 650 | 650 |  |  |  |  | Contingency
Contingency | 5% of planned spend |  | 2200 | 0 | 0
Total
[10 empty] | Cost per head | Value
Attendees expected (confirmed + registered)
Planned cost per head
Actual cost per head
Attendee fees invoiced
Attendee fees received
Net position (received - actual spend)

## Suppliers
Suppliers
Vendors, contacts and contract deadlines. Type A-G, I, L and O. The lead time from the event, the countdown and the flag are calculated.
Supplier | Category | Contact | Email | Phone | Contract value | Deposit paid | Balance due | Contract deadline | Lead from event (d) | Days to deadline | Status | Flag | Booked on Budget | Notes | Suppliers | Value
Northgate Hall | Venue | R. Aiken | events@northgatehall.example | 020 7946 0101 | 11300 | 3390 |  | 2026-06-12 |  |  | Contracted |  |  | Cancellation charges from 60 days out — the reason this one is critical. | Suppliers listed
Bellhouse Catering | Catering | D. Bell | hello@bellhouse.example | 020 7946 0142 | 12900 | 2580 |  | 2026-09-03 |  |  | Contracted |  |  | Final numbers 7 days before. The guarantee is what gets invoiced, not the turnout. | Contracted or confirmed
Stagecraft AV | AV & production | P. Osei | bookings@stagecraft.example | 020 7946 0177 | 7400 | 3700 |  | 2026-08-13 |  |  | Contracted |  |  | Rig the evening before; needs venue access from 18:00. | Still only quoted or shortlisted
Quickprint Ltd | Print | S. Mott | studio@quickprint.example | 020 7946 0190 | 1600 | 0 |  | 2026-09-07 |  |  | Shortlisted |  |  | Three working days from artwork approval. | Total contract value
Deposits paid
Balance still to pay
Deadline inside 14 days
Deadlines already passed
Earliest deadline
Formulas:
Days to deadline = IF(OR([Supplier]="",[Contract deadline]=""),"",[Contract deadline]-TODAY())
Flag = IF([Supplier]="","",IF([Contract deadline]="","No deadline set",IF([Status]="Confirmed","",IF([Contract deadline]<TODAY(),"DEADLINE PASSED",IF([Contract deadline]-TODAY()<=14,"Decide now","")))))

## Attendees
Attendees
The registration list. Type A-J and M. Balance and the needs flag are calculated; the counts to the right are what catering and access get.
Name | Organisation | Email | Ticket | Registered | Status | Dietary | Access needs | Fee | Paid | Balance | Needs check | Notes | Headcount | Value
J. Alvarez | Meridian Group | j.alvarez@meridian.example | Standard | 2026-07-14 | Confirmed | Vegetarian |  | 250 | 250 |  |  |  | Rows on the list
P. Nkemelu | Kestrel Ltd | p.nkemelu@kestrel.example | Early bird | 2026-07-13 | Confirmed | None | Step-free access to the stage | 180 | 180 |  |  |  | Confirmed
R. Lindqvist | Halcyon SA | r.lindqvist@halcyon.example | Speaker | 2026-07-20 | Confirmed | Gluten-free |  | 0 | 0 |  |  | Afternoon keynote | Registered, not confirmed
T. Whitaker | Ardent BV | t.whitaker@ardent.example | Standard | 2026-08-02 | Registered | None |  | 250 | 0 |  |  | Invoice sent 2026-08-02 | Waitlist
Cancelled
Catering count (confirmed + registered)
With a dietary requirement
With an access requirement
Fees invoiced
Fees received
Outstanding
Attended on the day
No-shows
No-show rate
[13 empty] | Dietary breakdown — the caterer's brief | People
Vegetarian
Vegan
Gluten-free
Dairy-free
Halal
Kosher
Nut allergy
None
Counts confirmed and registered only, because that is the number the caterer is given seven days out and the number that gets invoiced.