## README
Gantt Chart Project Planner
Free template from spreadsheet.partners — free for commercial use, no attribution needed.
What this workbook is for
Planning work where one thing has to finish before another can start. A Gantt chart drawn by colouring cells is a picture: it is right on the day you draw it and wrong by the end of the week. Here the only date anyone types is the project start. Every task start, every end, the critical path and every bar on the Chart tab are derived from the durations and the predecessors, so a task that takes five days longer than planned moves everything downstream of it by itself.
How to add a task
Type the name in column A, the duration in working days in column D, the owner and the per cent complete. If it can only start after another task, type that task's number — column G, not the spreadsheet row — in column B. Leave B empty or type an em dash for work that can start at the project start. Column H then shows the predecessor's NAME: if that is not the task you meant, the number is wrong, and it is easier to see there than in the dates.
The one rule: a task is listed below the task it depends on
Task 7 may depend on task 3, but not on task 12. This is how the forward pass avoids a formula that reads its own column and how the backward pass avoids one that reads its own row — both of which Excel refuses as circular references. Column M says so plainly if you break it. Reordering is safe: insert a row inside rows 5 to 204, copy the formulas down from the row above, and fix the predecessor numbers, which are positions in the list and shift when the list does. Do not copy a formula from row 6 UP into row 5 — row 5 is the first task and has its own, shorter version.
Working days, and why not WORKDAY()
A 10-day task starting on a Friday finishes in two weeks, not on the following Monday. Plans built in calendar days are optimistic by roughly the number of weekends they contain. The Calendar tab counts the days: one row per calendar day, a 0 or 1 for whether it is a working day after consulting the Holidays tab, and a running working-day number. A task's start and end are that number plus arithmetic, and the date you see is a lookup back into the calendar. WORKDAY() would be one function instead of a tab, and it behaves differently in Excel 2016 and Google Sheets once holidays are supplied as a range.
Slack, and what it is for
Slack is how many working days a task can slip before the project finish date moves. Zero slack means the task is on the critical path. The number in the column is total float, not free float: it accounts for everything downstream of the task, so a task whose successor has three weeks of room shows three weeks of room itself. Two tasks running late in the same week are not the same event — the one with zero slack costs you the launch date, the one with eighteen days of float costs you nothing. Escalate the first and leave the second alone.
Milestones
A task with a duration of 0 is a milestone: it lands on a single day, the day its predecessor finishes. Give it a predecessor and no owner. It appears on the chart as a one-cell bar and, having no successors, it carries whatever slack remains to the project finish.
Holidays
The Holidays tab feeds every date calculation. Add your own public holidays and any company shutdown before trusting a plan that crosses December. A holiday that falls at a weekend changes nothing and the tab says so, which saves the usual round of adding eleven dates and wondering why the finish date did not move.
Reading the chart
The Chart tab shows one column per period, seven days wide by default. Type the first date in C3 and the days per column in G3: 7 shows a year across the screen, 1 shows the next two months day by day. Green blocks are tasks with float. Red blocks are the critical path. The dark red column header is the period containing today. Nothing on that tab is a source of anything — it reads the Tasks tab, and editing a bar does nothing at all.
The Critical path tab
The same tasks, listed, with their owners and status. It is the escalation list. A task leaves it as soon as some other chain becomes longer, which is the correct behaviour and occasionally a surprise: the critical path is a property of the plan as it stands today, not a permanent label on the work you consider important.
One predecessor per task
The model is finish-to-start with a single predecessor, which covers most projects and keeps every formula readable. Work that genuinely waits on two things needs a MAX over both end dates; if you need that, or start-to-start links, lags, or resource levelling, it is a small change and we are happy to make it as a custom build.
The rows already in the file
The page's own example: discovery, design, build, content and a launch milestone, starting 1 September 2026. Design and build have no float and content has several weeks of it, which is the point of the example — two tasks running late in the same week are not the same event. Delete the rows and type over them; the formulas run to row 204 already and do not need copying down.
Which cells you type
Tasks: the project start in C3, then columns A, B, D, I, J and N. Chart: C3 and G3. Holidays: A, B and E. Nothing on the Calendar or Critical path tabs is typed, and the grey columns O to R on the Tasks tab are the working-day numbers the dates are built from — they are visible so the arithmetic can be checked, not so it can be edited.
Ranges
Tasks holds 200 rows, the Chart renders the first 100 of them, the Critical path tab lists up to 60, Holidays holds 100 dates and the Calendar covers two years from the project start. All of those extend by selecting the last row and dragging down. Work inside the ranges rather than below them: a task typed in row 205 is in no total, no chart and no critical path.
Blue text on a yellow fill = type here. Black = calculated, leave alone.

## Tasks
Tasks
Type the task, its predecessor's number, the duration in working days, the owner and the per cent complete. Dates are calculated — a date you type is a date that stops moving when the plan moves.
Project start |  | 2026-09-01 |  | The first working day on or after this date is working day 1. Everything else is counted from there.
Task | Pred. | Start | Days | End | Slack | # | Predecessor task | Owner | % complete | Critical | Status | Check | Notes | Start # | End # | Chain end # | Crit. # | The plan | Value
Discovery | — |  | 10 |  |  |  |  | A. Duval | 100% |  |  |  | Stakeholder interviews and content audit |  |  |  |  | Project start (typed)
Design | 1 |  | 15 |  |  |  |  | K. Owens | 60% |  |  |  | Wireframes, then visual design |  |  |  |  | First task starts
Build | 2 |  | 30 |  |  |  |  | S. Novak | 0% |  |  |  | Front end and CMS templates |  |  |  |  | Project finishes
Content | 1 |  | 20 |  |  |  |  | M. Ferrer | 35% |  |  |  | Runs alongside design — has float, see Slack |  |  |  |  | Tasks in the plan
Launch | 3 |  | 0 |  |  |  |  | A. Duval | 0% |  |  |  | Milestone: 0 days, so it lands on Build's last day |  |  |  |  | Tasks on the critical path
Working days, start to finish
Calendar days, start to finish
Working days of critical work
Complete, weighted by duration
Tasks complete
Tasks in progress
Tasks overdue
Most float on any one task
Rows with a problem
Calendar days minus working days is the weekend and holiday time the plan spends waiting. It is usually about 40% of the elapsed period, which is the whole argument for not planning in calendar days.
Formulas:
Status = IF([Task]="","",IF(J5>=1,"Complete",IF(AND([End]<>"",[End]<TODAY()),"Overdue",IF(AND([Start]<>"",[Start]<=TODAY()),"In progress","Not started"))))

## Chart
Chart
The Gantt rendering. Nothing here is typed except the first date and the days per column — every bar is a reading of the Tasks tab.
First column starts |  | 2026-08-31 |  | Days per column | 7 | 7 gives a year across the sheet; 1 gives a day-by-day view of the next two months. Green is a bar, red is a bar on the critical path.
Task | Start | End | Slack
The chart renders the first 100 tasks of the 200 the Tasks tab holds. To show more, copy row 104 down; to show a different period, change C3. The column highlighted dark red in the header is the one containing today.

## Critical path
Critical path
Every task with zero slack, in order. Nothing is typed here. These are the only tasks whose lateness moves the finish date, and the only ones worth escalating.
Tasks on it |  |  |  | Working days of critical work |  |  |  | Critical work finishes
# | Task | Start | End | Days | Owner | % complete | Status | Slack | Runs after
A task drops off this list the moment something else becomes longer than it. That is the point: the critical path is a property of the current plan, not a label you attach to important work.

## Holidays
Holidays
Non-working days. Every date on the Tasks tab is counted around these. Type the date and what it is; the rest is calculated.
Date | Holiday | Day | Effect | Notes | In this list
2026-12-24 | Christmas Eve |  |  | Half the team is out anyway | Measure | Value
2026-12-25 | Christmas Day |  |  |  | Dates listed
2026-12-28 | Boxing Day (substitute) |  |  |  | Actually remove a day
2026-12-29 | Company shutdown |  |  | Office closed between the holidays | Falling at a weekend
2026-12-30 | Company shutdown |  |  |  | Earliest
2026-12-31 | Company shutdown |  |  |  | Latest
2027-01-01 | New Year's Day
Holidays only bite inside the period the plan covers, and only on weekdays. Add your own public holidays and any shutdown week before you trust a date that crosses December.

## Calendar
Calendar
The working-day counter every date on the Tasks tab is read from. Nothing here is typed. Two years of days, starting at the project start.
Date | Day | Working day? | Working day # | Why this tab exists
WORKDAY() and WORKDAY.INTL are the obvious functions for this, and they are the two functions in the whole file that Excel 2016 and Google Sheets do not agree about once a holiday range is involved. Counting the days explicitly costs a tab and removes the disagreement.
It covers 730 calendar days — about two years. A plan that runs past the last row shows an empty Start and a warning in the Check column on the Tasks tab; select row 734 and drag down to extend it.