## README
Kanban Board for Task Management
Free template from spreadsheet.partners — free for commercial use, no attribution needed.
What this workbook is for
Running a board that can answer questions a whiteboard cannot: how long cards sit, in which column they sit, how much each person has on, and how long the queue will take to clear. If you only want to see the work, a dedicated kanban tool is a better board. The case for a spreadsheet is that the history stays in a form you can do arithmetic on.
How to move a card
Change the Column in C and the Entered date in D at the same time. D is the day the card entered the column it is in now, not the day it was created — that is column I. Getting this wrong is the one way to make the whole file lie, because every age and every ageing flag reads column D. Change them on the Cards tab: the Board tab is a view and typing over a formula there breaks the cell.
When a card is finished
Cut the row out of Cards and put it on the Done tab with its four dates — created, started, entered review, done. The archive is where cycle time comes from, and cycle time is what makes a forecast possible. Cards left sitting in a Done column on the board inflate every average on the file.
WIP limits
G3 on the Cards tab is the limit per person for work in progress. Start at one or two and lower it if throughput does not fall. High WIP feels productive and lengthens cycle time for everything, including the item you switched to. The ⚠ in column F fires when somebody is over; it is the mechanism that makes this a kanban board rather than a to-do list with columns.
Cycle time, lead time and age
Cycle time runs from entering In progress to Done: it is what the team controls. Lead time runs from creation to Done: it is what the requester feels. Age is how long the card has been in its current column right now. Backlog age is real but not actionable — a card can sit in the backlog for a year without anything being wrong.
Reading the stage block on Metrics
Average days in progress against average days in review is the first thing to look at. A team with a healthy-looking board and a two-week delivery time found 1.2 days in progress and 6.8 in review, because review was one person's part-time responsibility. A second reviewer more than halved end-to-end time without changing how any of the work was done. Nothing on a physical board would have shown that.
The 'as at' date
C3 on the Cards tab says =TODAY(), so ages are live. It is the one yellow cell in the file with a formula in it, and it is meant to be typed over: put 2026-07-14 in it and the board reads as it stood on that day, which is how you check whether last month's ageing problem is actually better.
Renaming the columns
Type the new names in row 3 of the Board tab, then update the drop-down on Cards column C (Data, then Data validation) to match. The five supplied are Backlog, Ready, In progress, Review and Done. Two formulas mention 'In progress' by name — the WIP flag on Cards and the in-progress counts on Metrics — so if you rename that one, change those too.
The rows already in the file
Nine cards and five finished ones from July 2026, which are the page's own example plus the two that put A. Duval over the WIP limit. Measured against today they are all months old, so put 2026-07-14 in C3 to see the board as the example describes it, then delete the rows and type your own over them.
Which cells you type
Cards: A, B, C, D, G, H, I, J, K and P, plus C3 and G3. Board: the column names in row 3. Done: A to G and M. Metrics: the owner names and the first week date. Everything else is calculated, and the two grey columns at the right of Cards are the lookup key the Board is built on.
Ranges
Cards and Done each hold 200 rows, the Board shows 25 cards per column and the weekly block covers 16 weeks. Work inside those ranges rather than below them. A board with more than 125 cards on it is not short of rows; it is short of a WIP limit.
Blue text on a yellow fill = type here. Black = calculated, leave alone.

## Cards
Cards
One row per card in play. Moving a card means changing the Column AND the Entered date — that pair is the only reason this beats a whiteboard.
As at |  |  |  | WIP limit per person |  | 2 |  | Ages are measured against C3. It says =TODAY(); type a date over it to see the board as it stood that day.
Card | Owner | Column | Entered | Age (d) | WIP flag | Type | Priority | Created | Started | Due | Days to due | Owner's cards here | Usual cycle (d) | Ageing | Notes | Slot | Board key
Rework checkout | A. Duval | In progress | 2026-07-02 |  |  | Feature | High | 2026-06-24 | 2026-07-02 | 2026-07-17
Add SSO | K. Owens | In progress | 2026-07-11 |  |  | Feature | Medium | 2026-06-30 | 2026-07-11 | 2026-07-31
Fix invoice PDF | M. Ferrer | Review | 2026-07-13 |  |  | Bug | High | 2026-07-06 | 2026-07-09 | 2026-07-15
Update docs | S. Novak | Backlog | 2026-06-20 |  |  | Chore | Low | 2026-06-20
Tidy webhook logs | A. Duval | In progress | 2026-07-09 |  |  | Debt | Low | 2026-07-01 | 2026-07-09
Refund edge case | A. Duval | In progress | 2026-07-13 |  |  | Bug | High | 2026-07-13 | 2026-07-13 | 2026-07-16
Carrier rate card | M. Ferrer | Ready | 2026-07-10 |  |  | Feature | Medium | 2026-07-02 |  | 2026-08-07
Search relevance | K. Owens | Backlog | 2026-06-29 |  |  | Feature | Medium | 2026-06-29
Nightly job alert | S. Novak | Review | 2026-07-08 |  |  | Support | High | 2026-07-01 | 2026-07-03 | 2026-07-10

## Board
Board
The board, as a view. Every cell is a lookup into the Cards tab — a card is moved there, never here. Rename a column in row 3 and it renames on Cards too.
| Backlog |  |  | Ready |  |  | In progress |  |  | Review |  |  | Done
# | Card | Who | Age | Card | Who | Age | Card | Who | Age | Card | Who | Age | Card | Who | Age
Under each column: how many cards are in it. Red means a card in that row has been sitting more than 14 days.
Where the work is
Column | Cards | Average age (d) | Oldest (d) | Over 14 days

## Done
Done
The archive. Cut a finished row out of Cards, paste the card name and owner here with its four dates, and the cycle time the rest of the file forecasts from is computed for you.
Card | Owner | Type | Created | Started | Entered review | Done | Cycle (d) | Lead (d) | In progress (d) | In review (d) | Week starting | Notes
Address validation | A. Duval | Feature | 2026-06-08 | 2026-06-15 | 2026-06-16 | 2026-06-23
Duplicate emails | K. Owens | Bug | 2026-06-11 | 2026-06-17 | 2026-06-18 | 2026-06-24
Bulk export | S. Novak | Feature | 2026-06-09 | 2026-06-22 | 2026-06-24 | 2026-07-02
VAT on invoices | M. Ferrer | Bug | 2026-06-25 | 2026-06-29 | 2026-06-30 | 2026-07-07
Archive old carts | A. Duval | Chore | 2026-06-26 | 2026-07-01 | 2026-07-02 | 2026-07-08
Four dates, not one. Created answers 'how long did the customer wait', Started and Done give cycle time, and Entered review is the one that turns 'delivery feels slow' into a sentence naming the column responsible.

## Metrics
Metrics
Cycle time and throughput, read off the Cards and Done tabs. Type the first week in B6 and the names in the owner block; nothing else here is typed.
Where the time goes
Stage | Average days | Longest | Cards measured |  |  |  | The board right now | Value
In progress | [6 empty] | Cards on the board
In review | [6 empty] | In progress
Start to done (cycle) | [6 empty] | Waiting in review
Created to done (lead) | [6 empty] | In the backlog
This block is the whole argument for the file. A team with a healthy-looking board and a two-week delivery time found 1.2 days in progress against 6.8 in review: review was one person's part-time job. A second reviewer halved end-to-end time without changing how the work was done. | [6 empty] | People over the WIP limit
Average age of a card (d)
By work type | [6 empty] | Oldest card (d)
Type | Done | Avg cycle (d) | Avg lead (d) | Longest (d) | Open now | In progress now | Cards sitting over 14 days
Feature | [6 empty] | Cards past their due date
Bug | [6 empty] | Cards finished, all time
Chore | [6 empty] | Finished in the last 4 weeks
Support | [6 empty] | Throughput, cards per week
Debt | [6 empty] | Average cycle time (d)
Days of work on the board at that rate
By owner | [6 empty] | The last line is Little's law: work in progress divided by throughput is how long the queue takes to clear. It is the number to quote when someone asks why their card has not started.
Owner | Cards on the board | In progress | Over the WIP limit | Oldest card (d) | Done all time | Avg cycle (d)
A. Duval
K. Owens
M. Ferrer
S. Novak
Throughput by week
Week starting | Cards done | Avg cycle (d) | Avg in review (d)
2026-06-01