## README
Meeting Notes & Action Items Tracker
Free template from spreadsheet.partners — free for commercial use, no attribution needed.
The rule this workbook is built on
An action needs an owner and a date, or it is not an action — it is a topic, and topics belong in the discussion notes. Rows on the Actions tab missing either are shaded across their width, because an action with no owner will never appear on anyone's list and nobody will ever be asked about it.
Why actions are one table and not one per meeting
Because the question people actually ask is 'what is M. Ferrer still holding', and that question has no answer if the actions are scattered across forty meeting records. One table, filterable by owner, by meeting or by status, is the whole idea. The Meeting and Date columns keep each action attached to the occasion it came from.
Status is typed once and shown twice
Column F is what the owner said. Column G is what is true today: an action still Open after its due date reads OVERDUE without anyone maintaining it. Every count on the Dashboard that says 'overdue' reads column G, and every count that says 'open' reads column F. Dropped is a legitimate answer and a better one than an action nobody intends to do sitting at Open for a year.
How to run the meeting with this open
Read the open actions at the START, by owner, from the first block on the Dashboard. A weekly operations meeting that kept revisiting the same three items had a 41% completion rate and, once the actions were in one table, four items that had been agreed twice under different wording. Moving the read-out from the end to the start took it above 80% within a month. Nothing else changed.
Why decisions are kept apart from actions
They have different readers at different times. An action is checked next week by the person who owns it. A decision is looked up in eight months by somebody asking why the thing was done this way, usually because the circumstances have changed. Mixed into the same list, neither is findable. The Why column is the one that earns the tab: a decision without its reason is re-argued from scratch every time, and the review date is there so a decision made under conditions that expire gets revisited on purpose rather than by accident.
Discussion notes
Keep them short. Nobody rereads them, and the effort spent on a verbatim record is effort not spent making the decision and action rows precise — those are the two parts with a future audience. Column G on the Meetings tab wraps, so a paragraph is fine and a transcript is waste.
The follow-up block
At the bottom of the Dashboard: type the meeting name and the date of the instance, and it lists that meeting's actions with a ready-made line in column F — '- Renegotiate DPD rates — M. Ferrer (due 2026-07-21)'. Copy the column into the mail. The obvious formula for this is TEXTJOIN, which Excel 2016 does not have and which would put all of them in one unreadable cell in any case.
Completion rate, and what counts
Done divided by every action raised, so dropped and blocked actions count against it. That is deliberate: a meeting that raises ten actions and drops six is not a meeting operating at 100%. The dropped and blocked counts sit next to the rate so the reason is visible. A rate around 40% is what a meeting that reads its actions at the end usually scores.
Person-hours
Present multiplied by minutes, on the Meetings tab. It is not an argument for cancelling the meeting; it is the number to weigh against what the meeting produced. A weekly 45-minute meeting for five people costs about 195 hours a year, which is a month of someone's working life and ought to generate more than three actions a week.
Automatic reminders
There is no macro in this file — a workbook that only opens when someone opens it cannot send anything. In Google Sheets an Apps Script trigger can mail each owner their open actions every Monday morning off the Actions tab, which is a short piece of automation and the single highest-return addition to this file.
The rows already in the file
Four meetings, nine actions and three decisions from July 2026, which are the page's own example. Their due dates are in the past, so most of them read OVERDUE — that is the mechanism working, not a fault. Delete the rows and type over them; the formulas are in every row to 204 and do not need copying down.
Which cells you type
Meetings: A to G, plus N and O. Actions: A to F, J, L and M. Decisions: A to I and L. Dashboard: the owner names, the meeting names and the follow-up meeting and date. Everything else is calculated, and the four grey columns at the right of Actions are the sequence numbers the Dashboard lists are built from.
Ranges
Meetings and Decisions hold 100 rows, Actions holds 200, and each Dashboard list shows 14 rows — enough for the overdue list to be embarrassing and not so many that it is ignored. Work inside those ranges rather than below them: an action typed in row 205 is in no count, no list and no follow-up mail.
Blue text on a yellow fill = type here. Black = calculated, leave alone.

## Meetings
Meetings
One row per meeting held. Type A to G. The action and decision counts are pulled from the other tabs — a meeting whose actions are never finished is visible here rather than in anyone's memory.
Meeting | Date | Attendees | Present | Minutes | Agenda | Discussion notes | Person-hours | Actions raised | Still open | Overdue | Completed | Decisions | Follow-up sent | Notes
Weekly ops | 2026-06-30 | A. Duval, K. Owens, M. Ferrer, S. Novak, R. Kaur | 5 | 45 | Ardent invoice; returns page; warehouse cover | Ardent 40 days late and not disputed. Returns page copy is wrong in two places. | [6 empty] | Yes
Weekly ops | 2026-07-07 | A. Duval, K. Owens, M. Ferrer, S. Novak, R. Kaur | 5 | 45 | Carrier rates; Q3 targets; PDP backlog | DPD rates up 8% from August. Q3 targets agreed; publishing them was the action. | [6 empty] | Yes
Board | 2026-07-09 | A. Duval, K. Owens, two non-executives | 4 | 90 | H1 numbers; hiring plan | H1 revenue 4% ahead of plan. Hiring paused until a plan exists on paper. | [6 empty] | Yes
Weekly ops | 2026-07-14 | A. Duval, M. Ferrer, S. Novak, R. Kaur | 4 | 40 | Open actions; PDP size chart; courier SLA | Open actions read at the START of the meeting for the first time. Two of them had already been agreed on 30 June under different wording. | [6 empty] | No

## Actions
Actions
Every action from every meeting, in one table. No owner and no due date means it is not an action — it is a topic, and it belongs in the notes.
Meeting | Date | Action | Owner | Due | Status | Status now | Days overdue | Owner's open actions | Closed on | Days to close | Priority | Notes | In meeting # | Meeting key | Overdue # | Due soon #
Weekly ops | 2026-06-30 | Chase the Ardent invoice | M. Ferrer | 2026-07-07 | Done |  |  |  | 2026-07-06 |  | Medium
Weekly ops | 2026-06-30 | Rewrite the returns page | S. Novak | 2026-07-10 | Open | [5 empty] | High
Weekly ops | 2026-06-30 | Confirm warehouse cover | K. Owens | 2026-07-03 | Dropped | [5 empty] | Medium
Weekly ops | 2026-07-07 | Renegotiate DPD rates | M. Ferrer | 2026-07-21 | Open | [5 empty] | High
Weekly ops | 2026-07-07 | Publish Q3 targets | A. Duval | 2026-07-14 | Done |  |  |  | 2026-07-13 |  | Medium
Board | 2026-07-09 | Draft the hiring plan | K. Owens | 2026-07-31 | Open | [5 empty] | Medium
Board | 2026-07-09 | Circulate the H1 pack | A. Duval | 2026-07-16 | Done |  |  |  | 2026-07-15 |  | Medium
Weekly ops | 2026-07-14 | Add a size chart to the PDP | S. Novak | 2026-07-28 | Open | [5 empty] | Medium
Weekly ops | 2026-07-14 | Review the courier SLA | M. Ferrer | 2026-07-24 | Blocked | [5 empty] | Medium
A row shaded orange across its width is missing an owner or a due date. It will never appear on anyone's list and nobody will ever be asked about it.
Formulas:
Status now = IF([Meeting]="","",IF(AND([Status]<>"Done",[Status]<>"Dropped",[Due]<>"",[Due]<TODAY()),"OVERDUE",[Status]))
Days overdue = IF([Status now]="OVERDUE",TODAY()-[Due],"")
Due soon # = IF([Meeting]="","",IF(AND([Status]="Open",[Due]<>"",[Due]>=TODAY(),[Due]<=TODAY()+7),COUNTIFS(F5:[Status],"Open",E5:[Due],">="&TODAY(),E5:[Due],"<="&TODAY()+7),""))

## Decisions
Decisions
What was decided, and why. Kept apart from actions because they are read at different times: an action is checked next week, a decision is looked up in eight months by somebody asking why it was done this way.
Meeting | Date | Decision | Why | Decided by | Affects | Review by | Status | Superseded by | Age (days) | Review due | Notes
Weekly ops | 2026-07-07 | Stay with DPD until the November review | An 8% increase is cheaper than switching carrier six weeks before peak. | A. Duval | Logistics | 2026-11-02 | Active
Board | 2026-07-09 | Hiring paused until the plan is approved | H1 is ahead but the Q4 pipeline is unproven; a hire made now is committed for a year. | Board | People | 2026-09-30 | Active
Weekly ops | 2026-06-30 | Returns handled in-house, not outsourced | Volume is below the third party's monthly minimum, so outsourcing costs more per return than doing it ourselves until volume roughly doubles. | M. Ferrer | Operations | 2027-01-11 | Active
The Why column is the one that earns its keep. A decision without its reason is a rule nobody can judge the expiry date of, and it gets re-argued from scratch every time the circumstances change.
Formulas:
Age (days) = IF([Meeting]="","",IF([Date]="","",TODAY()-[Date]))
Review due = IF([Meeting]="","",IF([Status]="Superseded","",IF([Review by]="","No review date set",IF([Review by]<TODAY(),"Review overdue",IF([Review by]<=TODAY()+30,"Review within a month","")))))

## Dashboard
Dashboard
Open actions by owner, completion rate by meeting, and the follow-up list. Type the names, the meeting names and the follow-up meeting; everything else is read off the other tabs.
Open actions by owner — the list to read at the START of the meeting
Owner | Actions | Open | Overdue | Done | Dropped | Completion rate | Oldest overdue (d) | Avg days to close | Everything, all meetings | Value
A. Duval | [8 empty] | Meetings held
K. Owens | [8 empty] | People-hours spent in them
M. Ferrer | [8 empty] | Actions raised
S. Novak | [8 empty] | Actions per meeting
R. Kaur | [8 empty] | Open
Overdue
Blocked
Dropped
Done
Completion rate
Average days to close
Actions with no owner or no date
Decisions recorded
Decisions still active
Decisions past their review date
Completion rate by meeting — a meeting whose actions never finish is a meeting with a problem | [8 empty] | A completion rate around 40% is normal for a meeting that reads its actions at the end. Reading them at the start, by owner, is the change that moves it above 80%, and it costs four minutes.
Meeting | Times held | Actions raised | Done | Open | Overdue | Completion rate | Avg days to close | Person-hours spent
Weekly ops
Board
Overdue now — oldest first is not the order here; this is the order they were raised in
# | Action | Owner | Meeting | Due | Days overdue
Due in the next seven days
# | Action | Owner | Meeting | Due
Follow-up for one meeting — type the meeting and its date, then copy column F into the mail
Meeting | Weekly ops | Date | 2026-07-14
# | Action | Owner | Due | Status now | Line to paste
Formulas:
Oldest overdue (d) = IF([Owner]="","",MAX(0,SUMPRODUCT(MAX((Actions!$D5:D204=[Owner])*(Actions!$F5:F204<>"Done")*(Actions!$F5:F204<>"Dropped")*(Actions!$E5:E204<>"")*(TODAY()-Actions!$E5:E204)))))