## README
Task & Workflow Manager
Free template from spreadsheet.partners — free for commercial use, no attribution needed.
What this workbook is for
Finding out where work waits. A status column tells you where something is now; a transition log tells you how long it took to get there, and only the second one can be used to fix anything. Log one row per state change and every status, age, queue length and bottleneck in the file derives itself.
The workflow
Draft -> Review -> Approved, with Review -> Rework -> Review as the loop back, and Cancelled reachable from any working state. Approved and Cancelled are terminal: they stop the end-to-end clock. The States tab holds that list and the allowed From/To pairs; change them there and the rest of the workbook follows. Keep the number of states small — if logging three or four rows per task feels like too much data entry, the workflow has too many states, not too much logging.
The rule for logging a transition
One row at the moment the work changes hands or changes state, with the real timestamp. Not at the end of the day, not reconstructed on Friday: an estimated timestamp measures nothing, and the waits are the entire point. If nobody will log at the moment, log only the handovers between people and accept that in-person moves are invisible — that is still better than a status column.
How the wait is calculated
Column F is the hours between this transition and the previous one for the same task, and column G shows exactly which timestamp it measured from so the number can be checked in a glance. The first transition of a task is measured from the Created timestamp on the Tasks tab, which is why that column matters: without it the first leg of every task would be invisible, and the first leg is usually the one being defended. Excel 2016 has no MAXIFS, so the previous timestamp is found with SUMPRODUCT(MAX(...)) — the same answer, entered normally, in both Excel and Google Sheets.
Why there is no status column to type into
Current state on the Tasks tab is the To of the most recent transition, so it cannot disagree with the history. Column H shows when the task entered that state and column I how many days it has sat there. A task whose current state is blank has no transitions logged at all, which the flag column says in those words.
Validating transitions
Column H on the Transitions tab flags a task that has no row on the Tasks tab — its first wait cannot be measured without a created timestamp — and any From/To pair that is not on the allowed list. It does not block anybody — a determined user will get round any rule — but it catches the typos that quietly make the metrics wrong: a state spelt two ways is two states, and the wait ends up in neither average. The dropdowns on From and To do most of that work already.
Reading the metrics
Average wait leaving each state is the bottleneck finder. In the worked example, a marketing team was sure content production was slow; the log showed drafting averaging about 6 hours and approval about 43, caused by one approver batching reviews into Friday. Moving to daily review slots cut end-to-end time from nine days to three without anybody drafting faster. The rework ratio — reworks over approvals — is the second number to watch: above about 20% the problem is the brief, not the execution.
What the numbers are not
The by-person block says who work waits on, not how fast anybody is. An approver with a long average wait is usually a person with one queue and no cover, and the fix is a second approver or a fixed review slot, not pressure. Used as a personal scoreboard, the log gets gamed: transitions get logged late, in batches, or with tidy timestamps, and the bottleneck disappears from the data rather than from the process.
Which columns you type
Transitions: A Task, B From, C To, D By, E At, K Note. Tasks: A-F and Q, plus the stalled threshold in C3. States: A-D for the states and I-K for the allowed pairs. Metrics: only the names in the by-person block. Everything else is calculated — yellow means type here, black means leave it alone.
Timestamps and dates
At and Created are date-and-time values, displayed as yyyy-mm-dd hh:mm. Type 2026-07-08 14:20 and Excel stores it as a number, which is what makes the subtraction work. Days in state and the overdue flag compare against TODAY(), so they move on their own; the seeded example rows are dated July 2026 and will read as long-stalled until you replace them.
Ranges
Transitions and Tasks cover rows 5-204, States 5-24 with 40 allowed pairs in I-L. Insert rows inside those ranges rather than typing below them, or the metrics will not see the new data. Transition rows do not need to be in date order: every formula finds the previous timestamp by value, not by position, so appending a forgotten transition in row 87 still produces the right waits.
Blue text on a yellow fill = type here. Black = calculated, leave alone.

## Transitions
Transitions
One row per state change. Type A-E and K; F onwards is calculated. Log the transition when it happens — a timestamp typed from memory on Friday measures nothing.
Task | From | To | By | At | Wait (h) | Measured from | Check | Latest | Key | Note
T-118 | Draft | Review | A. Duval | 2026-07-08 14:20 | [5 empty] | Brief ready for review
T-118 | Review | Approved | M. Ferrer | 2026-07-10 09:05 | [5 empty] | Approved in the Friday batch
T-119 | Draft | Review | K. Owens | 2026-07-09 11:40
T-119 | Review | Rework | M. Ferrer | 2026-07-09 16:15 | [5 empty] | Tone of voice — second paragraph
T-119 | Rework | Review | K. Owens | 2026-07-10 14:00 | [5 empty] | Rewritten
T-119 | Review | Approved | M. Ferrer | 2026-07-13 09:10 | [5 empty] | Waited over the weekend
T-120 | Draft | Review | S. Novak | 2026-07-08 15:24
T-120 | Review | Approved | M. Ferrer | 2026-07-10 10:30 | [5 empty] | Friday batch again
T-122 | Draft | Review | S. Novak | 2026-07-13 11:20

## Tasks
Tasks
The register. Type A-F and Q; there is deliberately no status column to type into — G onwards is derived from the transition log.
Stalled after (days in one state) |  | 3 |  | Only non-terminal tasks are ever flagged stalled.
Task | Title | Created | Owner | Priority | Due | Current state | In state since | Days in state | Moved by | Transitions | Total wait (h) | Reworks | Done | End to end (h) | Flag | Notes
T-118 | Campaign brief — autumn launch | 2026-07-08 08:08 | A. Duval | High | 2026-07-15 | [10 empty] | Waiting on the brand sign-off
T-119 | Landing page copy | 2026-07-09 08:34 | K. Owens | Medium | 2026-07-17 | [10 empty] | Came back once for rework
T-120 | Product one-pager | 2026-07-08 09:30 | S. Novak | Medium | 2026-07-20
T-121 | Case study — Meridian | 2026-07-13 09:00 | A. Duval | Low | 2026-07-24 | [10 empty] | Not started: no transition logged yet
T-122 | Pricing page update | 2026-07-13 08:45 | S. Novak | High | 2026-07-16 | [10 empty] | Sitting in review
Formulas:
Days in state = IF([In state since]="","",ROUND(MAX(0,TODAY()-[In state since]),1))
Flag = IF([Task]="","",IF([Transitions]=0,"No transition logged",IF([Done]="Yes","Done",IF(AND([Due]<>"",[Due]<TODAY()),"Overdue",IF([Days in state]>Tasks!$C3,"Stalled in "&[Current state],"In progress")))))

## States
States
The workflow itself: the states on the left, the transitions allowed between them on the right. Type A-D and I-K; the counts are calculated.
State | Order | Terminal | What it means | Tasks here now | Transitions out | Transitions in | From | To | Why it exists | Times used
Draft | 1 | No | Being written. The task owner holds it. |  |  |  | Draft | Review | The only way out of drafting.
Review | 2 | No | Waiting on somebody else. This is where queues form. |  |  |  | Review | Approved | Sign-off.
Rework | 3 | No | Sent back with comments. Back with the task owner. |  |  |  | Review | Rework | Sent back. Count these: they are the rework ratio.
Approved | 4 | Yes | Done and signed off. Terminal. |  |  |  | Rework | Review | Resubmitted after changes.
Cancelled | 5 | Yes | Dropped. Terminal, and worth counting. |  |  |  | Rework | Draft | Rewritten from scratch rather than edited.
[7 empty] | Approved | Rework | Reopened after approval — rare, and worth seeing.
[7 empty] | Draft | Cancelled | Dropped before anybody else spent time on it.
[7 empty] | Review | Cancelled | Dropped in review.
[7 empty] | Rework | Cancelled | Dropped rather than rewritten.
A transition logged outside this list is flagged on the Transitions tab rather than blocked. If a pair keeps appearing, the workflow has changed and the list is what should change with it.

## Metrics
Metrics
All calculated. Type only the names in the by-person block — everything else comes from the transition log.
Measure | Value
Tasks registered
Transitions logged |  |  | Compare the average wait leaving each state below. The state with the longest wait is the bottleneck, and it is usually not the one people name.
Tasks finished
Tasks in flight
Tasks with nothing logged
Tasks overdue
Average wait per transition (h)
Longest single wait (h)
Total hours waited
Approvals
Reworks
Rework ratio
Average end to end (h), finished tasks
Average end to end (days), finished tasks
Transitions outside the allowed list
By state — where the work waits
State | Tasks here now | Transitions out | Average wait leaving (h) | Total hours waited | Share of all waiting | Transitions in
By person — who the work waits on, not how fast anybody is
Person | Transitions made | Average wait before their move (h) | Hours held in total | Approvals | Sent back for rework | Tasks they own
A. Duval
K. Owens
M. Ferrer
S. Novak